## Sheet1
Outbound Campaign Activities
| TASK | Start Date | Expected End Date | End Date | Status
Admin
| Login & Logout | 2022-05-17 | 2022-05-17 | 2022-05-17 | Completed
login page of the User and Admin
Customer CRUD operations
| New Customer Adding , Deleting & Updation | 2022-05-17 | 2022-05-17 | 2022-05-17 | Completed
Campaign Mapping
| Map campaigns to customers | 2022-05-18 | 2022-05-18 | 2022-05-18 | Completed
User Campaigns
| show mapped campaigns of each customer | 2022-05-18 | 2022-05-19 | 2022-05-19 | Completed
First Review |  | 2022-05-19
User
Add Contacts
| CSV file upload |  |  |  | Completed
| single contact upload | 2022-05-19 | 2022-05-20 |  | Completed
Contact Status
| Status of each contacts to display in contact list table | 2022-05-23 | 2022-05-23 |  | Completed
Second Review |  | 2022-05-23
Close Contact
Closing the contact from the contact list.
| Update Status of Contact | 2022-05-23 | 2022-05-23
| Audit | 2022-05-23
Window Service
Uploads the contacts from local database to Avaya
| Update the status of contact. | 2022-05-23 | 2022-05-26
Test Application |  | 2022-05-26